Award Close-out – Interim Process

This interim process's purpose is to provide guidance on the award close-out process and responsibilities between the College Research Administrators and the Grants & Contracts Financial Services Office while an SOP is being generated.

# Team Responsibilities:

Research Administrators:

- Initiate Award Closeout

- Confirm final expenditures with PI as final

- Confirm all cost share obligations have been met

- Confirm all reconciliations are completed

- Confirm all personnel funding is updated off the award

- Confirm with PI all non-financial milestones have been sent

- Provide fixed price residual cost center for PIs

- Fill out Award Close Out Form

- Document if there is cost share on award

Grant Accountants (GCFS):

- Complete financial award closeout

# Process:

- PI and PAA receive an email from Research IT notifying them about an award expiring soon.

- RA verifies with PI and BSC the following:

With PI:

- All Expenses (including subaward expenses) on the Award are accurate and final. Provide Summary and detailed financial report for PI review.

- Confirm all cost share obligations have been met

- All deliverables have been completed and accepted by the Sponsor – This includes, but is not limited to: Programmatic Deliverables, and Final Progress Reports.

With BSC:

- Confirm SAHARA reconciliations are completed

- Personnel fund source has been updated.

- RA completes the Award Close-out form and emails GCFS requesting the closeout. Please attach PI and BSC confirmations of items listed in #1.

Subject Line: Award Closeout Request: PI [PI Name]; Award [SAT000XXX]

- GCFS process award closeout.

For fixed price awards residual balances refer to: https://www.utsa.edu/hop/chapter10/10.14.html